## Sheet1
Professional team | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: Project design Manager: Liu Xinran | Sun Ruotong Wang Shizheng Qi Te Liu Huiyang Zhang Juncheng
Task 1.1: Define user requirements
Task 1.2: Specify functionalities
Task 1.3: Design UI
Task 1.4: Optimize UI
WP 2: Architecture and interface design Manager: Sun Ruotong | Liu Xinran Wang Shizheng Qi Te Liu Huiyang Zhang Juncheng
Task 2.1: Evaluate function feasibility
Task 2.2: Conduct functional descriptions
Task 2.3: Design interface documentation
Task 2.4: Design database
Task 2.5: Select technology stack
WP3: Implementation of front-end information acquisition function Manager: Wang Shizheng | Sun Ruotong Liu Xinran Qi Te Liu Huiyang Zhang Juncheng
Task 3.1: Implement interface
Task 3.2: Implement the sustainable development guide function
Task 3.3: Implement community service query function
Task 3.4: Realize the integration function of community education resources
Task 3.5: Optimize completed code
Task 3.6: Joint debugging of front-end and back-end
WP4: Front-end interactive function logic implementation Manager: Qi Te | Sun Ruotong Liu Xinran Wang Shizheng Liu Huiyang Zhang Juncheng
Task 4.1: Implement interface
Task 4.2: Implement user system functions
Task 4.3: Realize owner resource management function
Task 4.4: Realize community employment platform function
Task 4.5: Optimize completed code
Task 4.6: Joint debugging of front-end and back-end
WP5: Backend implementation and deployment Manager: Liu Huiyang | Sun Ruotong Liu Xinran Wang Shizheng Qi Te Zhang Juncheng
Task 5.1: Implement interface
Task 5.2: Handle database operations
Task 5.3: Implement all classes
Task 5.4: Optimize completed code
Task 5.5: Joint debugging of front-end and back-end
WP6: Testing and documentation Manager: Zhang Juncheng | Sun Ruotong Wang Shizheng Qi Te Liu Huiyang Liu Xinran
Task 6.1: List all function points to be tested
Task 6.2: Test all function points
Task 6.3: Deploy to server
Task 6.4: Write usage documentation
add or remove work packages and tasks as necessary | [14 empty] | Deliverable
Milestone